## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
90 | As a developer, create Initial SRS Document so we better define the requirments | Create UI Mockup under 3.1 | 1 | Complete | UI Design | 2 | 0 | Graham
|  | Create functional requirements |  | Complete | Documentation | 3 | 0 | Brennan 75% Owen 25%
|  | Create non-functional requirements |  | Complete | Documentation | 3 | 0 | Troy 70%, Brennan 30%
91 | As a developer, create initial Product Backlog document so we can start adhering to scrum | Copy existing user stories | 1 | Complete | Documentation | 2 | 0 | Brennan, Troy, Owen, Graham
|  | Categorize user stories on priority |  | Complete | Documentation | 2 | 0 | Brennan, Troy, Owen, Graham
92 | As a developer, create and upload initial framework of backend and frontend of app | Create React Front-end | 1 | Complete | Front-end Programming | 2 | 0 | Troy
|  | Create Express Back-end | 1 | Complete | Back-End Programming | 2 | 0 | Troy
|  | Create Postgresql server | 1 | Complete | Back-End Programming | 2 | 0 | Troy
|  | Create installation readme file | 1 | Complete | Documentation | 1 | 0 | Troy