## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
23 | Record Presentation | Practicing Presentation | 2 | Complete | preparation | 4 | 4 | Everyone
|  | Actual Recording of Presentation | 2 | Complete | Marketing | 3 | 3 | Troy and Owen
24 | Discuss Target audience |  | 2 | Complete | Preparation | 1 | 1 | Everyone
25 | Create Presentation | Create overview slides | 2 | Complete | Preparation | 2 | 2 | Brennan, Troy
|  | Refine Taskflow/Wireflow | 2 | Complete | Consolidation | 3 | 3 | Owen, Graham
26 | Complete SRS Document | Fill in missing sections, refine current sections | 2 | Complete | Documentation | 3 | 3 | Brennan, Troy
27 | Architecture Design Document |  | 2 | Complete | Documentation | 2 | 2 | Troy
28 | Use Case Diagrams/Models Document |  | 2 | Complete | Documentation | 4 | 4 | Graham, Owen, Brennan
29 | Create Front Page UI | Login Component | 2 | Complete | Programming | 5 | 1 | Brennan, Graham
|  | Search Bar | 2 | Complete | Programming | 5 | 0 | Brennan, Graham
|  | Sign Up Component | 2 | Complete | Programming | 5 | 0 | Brennan, Graham
|  | Help Button | 2 | Complete | Programming | 5 | 0 | Brennan, Graham