## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
30 | Revise SRS doc | Complete Greg's comments | 3 | Complete | Documentation | 1 | 1 | Graham
|  | Remove template descriptions | 3 | Complete | Documentation | 1 | 1 | Graham
31 | Update Architecture Design Doc | Revise Doc from Greg's comments | 3 | Complete | Documentation | 1 | 1 | Troy
32 | Revise Use Case Models and Descriptions | Revise Models | 3 | Complete | Documentation | 3.5 | 3.5 | Owen
|  | Revise Descriptions | 3 | Complete | Documentation | 3.5 | 3.5 | Owen
33 | Sequence Diagrams | Creating Sequence Diagrams Doc | 3 | Complete | Documentatinon | 7 | 7 | Troy
34 | NavBar | Login Component | 3 | In Progress | Programming | 8 | 1 | Brennan
|  | Sign up Component | 3 | In Progress | Programming | 9 | 1 | Brennan
35 | Match System | Match System Component | 3 | In Progress | Programming | 12 | 0
36 | Front end Design | Switching to Typescript | 3 | Complete | Programming | 1 | 1 | Brennan/Troy